Food Wise 2025 – First High Level Implementation Committee (HLIC) Meeting

30th September 2015

Attendance:

DAFM: Minister Coveney, Secretary General Aidan ODriscoll, Bríd Cannon, Brendan Gleeson, Cecil Beamish, Josephine Kelly and Áine Kilroy

State Bodies: Gerry Boyle, (Teagasc), Aidan Cotter (Bord Bia), Michael Cantwell (EI), Tara McCarthy (BIM) and Dara Lynott (EPA)

Other Government Depts: David Walsh (DECLG), Ray O'Leary (DTTAS), Clare Dunne (DJEI) and Finbarr Kelly (DPER).

Secretariat (DAFM): Sinéad McPhillips, Damien Flynn and Siobhán Dowling

This was the first meeting of the HLIC of Food Wise 2025. Minister Coveney welcomed the committee members, particularly those who had not been part of the previous HLIC for Food Harvest.

1. Food Wise 2025 Implementation process

Food Wise 2025 implementation will be driven by this High Level Implementation Committee (HLIC), as was the case for Food Harvest 2020, but with an expanded membership of senior officials from other Government Departments and relevant State Agencies. The secretariat will be provided by Economics and Planning Division in DAFM. Membership is in a personal capacity – substitutions to be avoided. Attendance required at each meeting will be determined by the agenda for the meeting for other Government Departments. Other officials, industry representatives and experts will be invited to participate in the work of the Committee in relation to specific topics.

It is planned to have quarterly meetings with the agenda set at the previous meeting. The next HLIC meeting will take place on 25th November at 9.30am and will deal with Sustainability. The final Environmental Analysis Report will have been published by then.

The Committee agreed that the Environmental Analysis Steering Group should continue their work with a broader scope of driving the sustainability recommendations of Food Wise and the finalised SEA and reporting back to the HLIC on a regular basis.  Bríd Cannon will chair this enlarged group, perhaps re-named as the Food Wise Sustainability Steering Group, which will include the relevant Departments and State Agencies.

It was also agreed that the other cross cutting themes of human capital, competitiveness, market development and innovation be dealt with at future meetings, with a specific sub-sector also on the agenda for each meeting.

2. Food Wise 2025 Recommendations

A paper was circulated outlining the 387 recommendations and actions in the Food Wise report, listing the number of actions under the cross-cutting and sectoral themes, and assigning lead ownership for all of the recommendations.

In many cases, there will be shared and over-lapping responsibilities, but it makes sense to assign a lead for reporting purposes.

It was agreed that the Department, agencies and Government Departments will report on the actions on a quarterly basis and that this be placed as an agenda item for discussion at future meetings.

The agencies highlighted their priorities to be achieved by the end of the year.

Enterprise Ireland:

- Drive the implementation of approved projects and new investments in 2015-2016

- Drive the Innovation research Development agenda with our client companies

- Drive the Management Capability and Competitiveness agenda with our client companies

BIM:

- Action 18 relating to the recruitment of fishermen and aquaculturalists into OG in partnership with Bord Bia and industry – although ongoing it will have significant milestones achieved in 2016

- Action 38 re the research and outputs related to landing obligations and discards

- Action 71 re certification process introduced to cover crew training and qualification on board fishing vessels

- Action 135 re Seafood industry and scaling investment

Teagasc:

1.   Food Hub in situ by the end of this year

2.   Review of green certs will commence within the next six weeks

Bord Bia:

1.   Action 182 establishing a Consumer Insight Centre with its own physical space could be put in place for January 2016

2.   Action 22 regarding verification of all members by end 2016 (which also would achieve nos. 339, 350, and 385) is a commitment that will be essential to maintain momentum behind Origin Green and its achievement would mark a major step forward for the programme. It is expected that a further 50 companies will be signed up to Origin Green by the end of this year.

3.   Increase presence of Bord Bia personnel in the Asian market.

3. Environmental Analysis of Food Wise 2025

Bríd Cannon gave an update on the Environmental Analysis of Food Wise 2025 (incorporating an Appropriate Assessment and a Strategic Environmental Assessment).

The final Report is being examined by the Environmental Analysis Steering Group; to be finalised following a meeting next week.

The final SEA will be discussed in detail at the next meeting on 25th November.

There was a discussion on sustainability in general and the following topics were highlighted:

- transport emissions,

- impact analysis by sector and by region,

- aligning with the various EU directives,

- carbon neutrality

- ambition to improve beef carbon footprint

- messaging on sustainability not just on agriculture but on sustainability in general.

Minister Coveney stressed the need to communicate sustainability not just under FW2025 and that Ireland needs to try and become the world leader on sustainability. This viewpoint was echoed by others on the Committee. These issues will be discussed in more detail at the 25th November meeting.

Siobhán Dowling

Economics & Planning Division

30 September 2015